## template
User Story | Issue # | Task# | Task assigned to | Estimated Effort | Actual Effort | Done (y/n) | Notes | Iteration:
project organization | 0 | [6 empty] | Project: | TA hiring system
Assignment 1 | 0 | [6 empty] | Group: | 17a
Assignment 2 | 0
Assignment 3 | 0
A user can login using a NetID and a password, so that they can securely access the application. | 3
Application starts instantly after a course has been created. | 9
Students can apply for becoming a TA | 1
Students should have passed the course before being able to apply for a position as a TA. | 10
Lecturers can view candidates' information, so that they can select their future employees. | 2
Lecturers can select candidates so that they will become TAs. | 4
Lecturers can rate their TAs, so that TAs can be recommended for their future applications. | 8
Lecturers gets an overview of past TA'ing experience and past-grades for their course, along with their ratings by other lecturers. | 7
The maximum capacity for a course is 1 TA for every 20 students. | 15
Students should only be able to TA a maximum of 3 courses per quarter. | 16
Students should only be able to apply and withdraw 3 weeks before the course starts. | 19
Students should only be able to withdraw 3 weeks before the course starts. | 20
Lecturers can only select candidates after the application closes (3 weeks before course start date). | 21
Students will receive a notification after the selection procedure has happened, so that they will know their results. | 14
Lecturers can receive recommendations of prominent TAs to help them in the selection procedure. | 22
Contract can be created containing the course name, the period, amount of hours and information on their tasks as a TA. | 17
After a student has been selected, they should be sent a contract containing the course name, the period, amount of hours and information on their tasks as a TA, so they can officially be hired. | 18
TAs can declare their hours, so that they can receive the correct payment. | 23
Declared hours should not exceed the hours on the contract of the course. | 24
Admin can delete courses, so he can manage the database. | 30
Admin can modify courses, so he can manage the database. | 31
Admin can add courses, so he can manage the database. | 32
Lecturers can enter task descriptions on the contract so that the TA will have an overview of the requirements. | 25
TA's can enter time spent on a course to give future TA's an idea of what is to be expected. | 26
Applicants should see the indication of how much time a course will take to TA. | 27
Hours declared should be approved by a lecturer, so that the lecturer has control over payment. | 28
The lecturer can view candidates based on a minimum grade preference. | 29

## sprint_2
User Story # | Task# | Task assigned to | Estimated Effort | Actual Effort | Done (y/n) | Notes | Column1 | Iteration: | 2
Project organization | Define requirements | Everyone | - | 2 | y
| Add issues to gitlab | Iarina | - |  | y
| Make project template | Vincent | - | 0.25 | y
Assignment 1 | Define bounded contexts | Everyone | - | 3.25 | y |  |  | Project: | TA hiring system
| Make UML diagram | Everyone | - | 2 | y | needs to be converted to lollipop |  | Group: | 17a
[8 empty] | note: | this sprint was made retroactively, so theres no estimated efforts

## sprint_3
User Story # | Task# | Task assigned to | Estimated Effort | Actual Effort | Done (y/n) | Notes | Iteration: | 3
Assignment 1 | convert UML to lollipop diagram | andrei | 1.5 | 1.5 | y | some feeback needs to be implemented | Project: | TA hiring system
| make draft for implementing design patterns | Ravi, andrei | 1.5 | 1.5 | y |  | Group: | 17a
project organization | Add todo's per issue in gitlab | iarina, gijs, vincent | 5
| make big class diagram | pauline | 2
| make sprint table for week 1,2,3, | pauline | 0.5

## sprint_4
User Story | Issue # | Task# | Task assigned to | Estimated Effort | Actual Effort | Done (y/n) | Notes | Iteration: | 4
project organization | 0 | [6 empty] | Project: | TA hiring system
| 0 | [6 empty] | Group: | 17a
0
Assignment 1 | 0 | make draft and diagrams for implementing design patterns | Ravi | [6 empty] | TA hiring system
| 0 | make draft for assignment 1 part 1 | pauline | 3 | 3 | y
Assignment 2 | 0
Assignment 3 | 0
A user can login using a NetID and a password, so that they can securely access the application. | 3
Application starts instantly after a course has been created. | 9
Students can apply for becoming a TA | 1
Students should have passed the course before being able to apply for a position as a TA. | 10
Lecturers can view candidates' information, so that they can select their future employees. | 2
Lecturers can select candidates so that they will become TAs. | 4
Lecturers can rate their TAs, so that TAs can be recommended for their future applications. | 8
Lecturers gets an overview of past TA'ing experience and past-grades for their course, along with their ratings by other lecturers. | 7
The maximum capacity for a course is 1 TA for every 20 students. | 15
Students should only be able to TA a maximum of 3 courses per quarter. | 16
Students should only be able to apply and withdraw 3 weeks before the course starts. | 19
Students should only be able to withdraw 3 weeks before the course starts. | 20
Lecturers can only select candidates after the application closes (3 weeks before course start date). | 21
Students will receive a notification after the selection procedure has happened, so that they will know their results. | 14
Lecturers can receive recommendations of prominent TAs to help them in the selection procedure. | 22
Contract can be created containing the course name, the period, amount of hours and information on their tasks as a TA. | 17
After a student has been selected, they should be sent a contract containing the course name, the period, amount of hours and information on their tasks as a TA, so they can officially be hired. | 18
TAs can declare their hours, so that they can receive the correct payment. | 23
Declared hours should not exceed the hours on the contract of the course. | 24
Admin can delete courses, so he can manage the database. | 30
Admin can modify courses, so he can manage the database. | 31
Admin can add courses, so he can manage the database. | 32
Lecturers can enter task descriptions on the contract so that the TA will have an overview of the requirements. | 25
TA's can enter time spent on a course to give future TA's an idea of what is to be expected. | 26
Applicants should see the indication of how much time a course will take to TA. | 27
Hours declared should be approved by a lecturer, so that the lecturer has control over payment. | 28
The lecturer can view candidates based on a minimum grade preference. | 29

## sprint_4 old
User Story # | Task# | Task assigned to | Estimated Effort | Actual Effort | Done (y/n) | Notes | Iteration: | 4
Assignment 1 | convert UML to lollipop diagram | andrei | 1.5 | 1.5 | y | some feeback needs to be implemented | Project: | TA hiring system
| make draft and diagrams for implementing design patterns | Ravi | 1.5 | 1.5 | y |  | Group: | 17a
project organization | Add todo's per issue in gitlab | iarina, gijs, vincent | 5 | 2 | n | almost done, will finish today
| make big class diagram | pauline | 2 | - | n
| make sprint table for week 1,2,3 | pauline | 0.5 | 0.5 | y
33 | make database connection | gijs, iarina | 2
?? | creating basic classes for components that don’t use design patterns | ravi

## sprint_5
User Story | Issue # | Task# | Task assigned to | Estimated Effort | Actual Effort | Done (y/n) | Notes | Iteration: | 5
project organization | 0 | basic controllers for application, making a planning for should requirements | iarina | 4 hours |  |  |  | Project: | TA Hiring System
Assignment 1 | 0 | [6 empty] | Group: | 17a
Assignment 2 | 0
Assignment 3 | 0
Students can apply for becoming a TA | 1 | 1,2,3,4 | vincent | 2-3 hours per task
| 1 | 4,5,6,7,8 | ravi | 2-3 hours per task
Students should have passed the course before being able to apply for a position as a TA. | 10 | 1.2 | ravi | 2-3 hours per task
Lecturers can view candidates' information, so that they can select their future employees. | 2 | 4 | pauline | 2-3 hours per task
| 3 | 3 | gijs | 2-3 hours per task
Lecturers can select candidates so that they will become TAs. | 4 | all, and make basic controllers | andrei | 2-3 hours per task
Lecturers can rate their TAs, so that TAs can be recommended for their future applications. | 8 | 1 | pauline | 2-3 hours per task
| 8 | 2.3 | gijs | 2-3 hours per task
Lecturers gets an overview of past TA'ing experience and past-grades for their course, along with their ratings by other lecturers. | 7 | 1 | pauline | 2-3 hours per task
| 7 | 4,5,6 | gijs | 2-3 hours per task
| 7 | 2.3 | iarina | 2-3 hours per task
The maximum capacity for a course is 1 TA for every 20 students. | 15
Students should only be able to TA a maximum of 3 courses per quarter. | 16
Students should only be able to apply and withdraw 3 weeks before the course starts. | 19
Students should only be able to withdraw 3 weeks before the course starts. | 20
Lecturers can only select candidates after the application closes (3 weeks before course start date). | 21
Students will receive a notification after the selection procedure has happened, so that they will know their results. | 14
Lecturers can receive recommendations of prominent TAs to help them in the selection procedure. | 22
Contract can be created containing the course name, the period, amount of hours and information on their tasks as a TA. | 17
After a student has been selected, they should be sent a contract containing the course name, the period, amount of hours and information on their tasks as a TA, so they can officially be hired. | 18
TAs can declare their hours, so that they can receive the correct payment. | 23
Declared hours should not exceed the hours on the contract of the course. | 24
Admin can delete courses, so he can manage the database. | 30
Admin can modify courses, so he can manage the database. | 31
Admin can add courses, so he can manage the database. | 32
Lecturers can enter task descriptions on the contract so that the TA will have an overview of the requirements. | 25
TA's can enter time spent on a course to give future TA's an idea of what is to be expected. | 26
Applicants should see the indication of how much time a course will take to TA. | 27
Hours declared should be approved by a lecturer, so that the lecturer has control over payment. | 28
The lecturer can view candidates based on a minimum grade preference. | 29